LEGCO QUESTION NO. 11

Property Developments in the Past Three Years

Involving Late Completion of Public Facilities

| Development | Developer | Public facilities required | Completion and handover of public facilities |  |
| --- | --- | --- | --- | --- |
|  |  |  | Date specified in land lease | Actual date |
| Kai Tak Garden, Choi Hung Road | Hong Kong Housing Society | Social centre for the elderly and home help centre | 30 September 2000 | 31 October 2001 |
| Cayman Rise, Ka Wai Man Road | Hong Kong Housing Society | Day care centre for the elderly | 30 September 2000 | 18 January 2001 |
| Nob Hill, Lai King Hill Road | Central More Ltd. | Public transport terminus | 1 November 2000 | 6 December 2000 |
| Broadview Court, Shum Wan Road | Century Metro Development Ltd. | Public transport terminus | 29 June 2000 (extended* to 29 January 2001) | 8 November 2001 |
| Island Resort, Siu Sai Wan Road | SilverLink Investment Ltd. | Public transport terminus | 31 March 2001 | 11 April 2001 |
| Leighton Hill, Wong Nai Chung Road | Harsco Ltd. | Community hall | 30 September 2001 | June 2002# |
| Grand Regentville, Wo Mun Street | Apex Speed Ltd. | Market, cooked food centre, indoor recreation centre, government offices and other community-related facilities | 31 December 2001 | 22 January 2002 |

*	A seven-month extension was granted to the developer on account of geotechnical constraint which could not have been foreseen by the developer.

#	Procedure for the handover of the community hall to Government is expected to be completed by the end of June 2002.